## Sheet1
Worksheet
Project Name:- Reinforcement learning with drift detection for Autonomous modeling in IoT Environment
TimeLine - 3 Months
Expected Outcome - A journal or Good Conference Paper
TimeLine | Task | Discussion | Remarks
2021-05-01 | Read out IoT/CyberPhysical System and IoT and OT Network(Literature Survey)
2021-05-04 | Collection of Dataset
1) Collecting IoT device and network dataset- available online
| 2) Collection of IoT binaries | Identify possible vulnerabilties using machine learning
3) Collection of any OT network dataset - specifically power grid or vehicular network
2021-05-11 | Analyze data set (Contain both Benign and Attack data) |  | Need to brushup Python and able to write python notebook
1) Cleaning of dataset
2) Extracting useful features
3) Finding patterns
2021-05-17 | Reading different machine learning models
1) Idea to work on reinforcement learning
| 2) Drift Detection and updating model to minimize drift and gain accuracy |  | DDM and EDDM
2021-05-25 | Training model
1) Offline training
2) Online training - important, as all OT system run in real time and attack detection should be done in real time
2021-06-01 | Results outcome
1) Comparing with state of the art or existing models
2) Showcasing why our model is more efficient and practical
2021-06-10 | Come up with draft of 6 - 8 pages (potential conference paper)
20-0602021 | Setup in-house environment to collect our own data
Future Work
2021-06-27 | 1) Collect in-house dataset
2021-07-03 | 2) Training the system with online dataset
2021-07-10 | 3) Selecting the same feature set and perform testing with inhouse dataset
2021-07-17 | Perform similar experiments.
2021-07-30 | Extended journal paper